Aquatic Gardeners’ Association Convention

Information for Prospective Hosts

Requirements

- General Information. This document is intended to aid a local organization (Local) that is considering submitting a proposal to host the Aquatic Gardeners’ Association (AGA) Annual Convention. Most of the information is provided as a guide to help the Local prepare a proposal and host the Convention. Certain items are necessary and are listed under section “2.Requirements.”  The Convention will take place beginning on a Friday afternoon and ending on Sunday. Proposals should be submitted to ___name_______, ___address_____________________. Only proposals received by __name___ not later than 5:00 p.m., ___date___ will be considered. The AGA Executive Committee selects the Convention host based on the quality and germaneness of listed speakers and other events, financial impact on the AGA, geographical location, the feasibility of the proposal, the strength & reputation of the local club, and the attendance cost to the members. The selection will be announced by mail, email, or telephone call.

- Requirements for Convention and Items to be Addressed in a Proposal

  - General Information Requirements

      - Hotel -- Size of hotel and other features that demonstrate its appropriateness for the Convention

      - Means of access to the hotel from the local airport, distance between airport and hotel, the availability of an airport shuttle service, closeness to major highways, etc.

      - Other local attractions or destinations of special interest (Public Zoos or Aquariums, museums, parks, fish/plant stores) to consider for field trips or Convention events

      - Other Convention Activities:

        - Provide outlines for tours or fieldtrips to be scheduled beyond the scheduled times of Convention activities, including fees, transportation options, meal options, etc.

        - Other events, such as roundtable Q & A sessions with the speakers, may be scheduled if time and resources permit.

  - Historical record

    - The Speaker Forums and Banquet presentations may be video taped to provide a historical record.

      - After the Convention, if a video has been recorded, it can be edited and copies produced for sale.

    - A Treasurer’s report to the AGA Executive Committee needs to provide a final accounting of costs, revenues, and distribution of funds after the Convention.

    - Recognition and thank you letters need to be sent to speakers, volunteers, corporate sponsors and others that donated any time, money, or goods to the Convention.

  - Finances

    - Any expenditure must be expressly approved by the AGA or its designee.

    - Registration Fees  -- the amount of the proposed Registration Fees

      - The discounts offered for early registration.

      - Collection of fees must be coordinated with work with the AGA website to ensure smooth integration with AGA's online payments.

    - Hotel

      - room charges for attendees

      - The contract document must be reviewed by the AGA Treasurer prior to execution.

    - Financial Plan -- Estimated Revenues and Costs

      - Costs by Item

        - Including hotel banquet room and other room charges (such as auction room), catering, speaker subsidies, advertising, expenses, name tags, auction bags, postage, etc.

      - Revenues by Item

        - Including fees, auction proceeds, raffles, etc.

    - Financial Sharing --  50/50 division of costs and revenues between AGA and the local organization

    - Donated Items to be used for the Aquascaping Contest

      - From the items donated to the convention, 7 items with the approximate values indicated below should be set aside to be used by AGA for prizes in the AGA Aquascaping Contest.

        - The six items for 1st Place need not be identical.

      - The specific items to be set aside for the Contest will be chosen jointly by the Convention Chair and the AGA Board of Director

      - These seven items should not be counted as part of the gross revenue of the Convention but as a “pass-through” to AGA

      - A representative of the AGA Aquascaping Contest, designated by the AGA Board of Directors will pick up the prizes at the Convention.

      - Value of Prizes

Prize	Approximate Value of each Prize	Number of Prizes

Best of show		$100	1

1st place		$50	6

  - Exhibits

    - Manufacturers/Vendors that will present exhibits

      - Negotiations with the manufacturers shall be handled by the Local.

    - Competition

      - If competitive exhibits are to be shown, describe the type of competition.

      - Awards for winners

  - Food

    - Banquet – Saturday night banquet

      - The Banquet may include announcements, awards, special recognitions, a guest speaker

    - Nearby restaurants

      - Distance from hotel

      - typical price range for meals

  - Speakers

    - No commitments as to dates or subsidies should be made on AGA’s behalf without its express approval. But a tentative list of those speakers that the Local proposes to seek should be listed.

    - The Convention should have at least 4 speakers that make individual presentations on Saturday

      - At least 3 of the speakers should speak directly about aquatic gardening.

  - Auctions

    - Plant Auction – Sunday morning auction to be run by the Local

      - the style of auction/bidding

        - This has been held as a silent auction, where bidders are allowed to bid as often as they wish within a time period and all bids are written and in public view.

        - “Live” auction, using an auctioneer can be an acceptable alternative.

      - percentage share of proceeds from each sale to the seller

    - Other auction(s) – For any other auction, for example, a fish and dry goods auction, that the Local wishes to include, describe the following.

      - Type of items to be auctioned

      - type of auction (see 2.7.1.1 above)

      - percentage share of proceeds from each sale to the seller

    - You need not be registered at the Convention to attend the auction

    - You must be a member of the Local or AGA to sell at the auction unless the sellers donate the proceeds in full to the Convention.

    - The host club is responsible for the entire auction including furnishing an auctioneer, setting up an accounting procedure, providing runners, etc

- Proposed Staffing

  - List of persons and distribution of responsibilities

    - At a minimum, a Convention Chairperson should be named

    - Contacts

      - That person that will act as the primary liaison between the Local and AGA regarding the Convention.

      - That person or those persons in the Local that can be contacted by AGA should the need arise

- Club Information

  - Describe your club's history, focus, number of members, and any other salient facts.

    - You may include any additional information that you feel is relevant to describing your organization and it’s abilities to sponsor the Convention.

Guidelines for Hosting AGA Convention

These Guidelines are intended to aid any prospective local organization (Local) that proposes to host an Aquatic Gardeners’ Association (AGA) Convention. It is provided as a guide but not as requirements – for requirements, see the Aquatic Gardeners’ Association Convention Information for Prospective Hosts –Requirements.

The Local should decide what number of staff will be useful and available to plan, organize, and conduct the Convention. The Local should decide also on the division of responsibilities. One person cannot do the job alone. It is suggested that the responsibilities, however divided, cover the following:

Convention ChairPerson – A single person should have responsibility for overall Convention planning, setting up committees, arranging meetings, establishing and enforcing milestones and deadlines. A chair should, as much as possible, allow those willing to work on the Convention undertake tasks that interests them and which most suits them. Handing out assignments early helps to avoid task mismatches.

Ideally, the Chair is also the Key liaison person with AGA Executive Committee, providing the AGA with frequent updates on the progress of the planning and organizing of the Convention, revenues and spending and budget performance.

CONVENTION PROGRAM

A convention program should be prepared and provided to each attendee when they check in at the registration desk. Consider having the Program professionally printed in color; the production may be too time-consuming for a volunteer to do and the cost of materials, including inkjet cartridges may prove to be nearly as costly as professional printing. In any event, the program should look professionally and artfully prepared. Consider having space in the program available for sale to sponsors for a reasonable fee in addition to their basic sponsorship. Do not underestimate how long it will take to prepare the Program.

Speaker biographies should be included in the Program. To do so, the material should be obtained well in advance of the Convention so tallow adequate time for layout and printing. A portion of the program should be used to inform attendees where they can go to get help or information that isn’t explicitly in the Program.

SPONSORSHIP

This job is too big for one person to do effectively and at least two to three people should be assigned this task as their major responsibility regarding the convention. An extensive number of telephone calls, visits to potential sponsors, and repeated contacts, will often be necessary to achieve a good level of sponsorship and donations. Be sure to solicit product donations for raffles. Have a list of prospective donors compiled, and then divide it into groups for specific types of sponsorship e.g. a) large companies for under-writing, advertising, b) smaller companies for trophy sponsorship, c) smaller companies for product donations. A different solicitation letter is then sent to members in each group.

An alternative is to produce one standard letter including all types of sponsorship and letting the addressee choose his/her type or types. Remember they would not appreciate receiving more than one letter requesting support. An all inclusive letter also is sometimes useful where a sponsor is amenable to supporting more than one area.

The areas needing donations are: a) money to cover speakers, publication and awards/trophies, b) raffle, c) auction, d) welcome bags, e) welcome bag items.

The solicitation letter should hit on the good points of the Convention, its speakers, hobbyists, etc. Make them aware that their name will be mentioned several times throughout the Convention and the number of people your advertising is expected to reach.

Make the prospective donors aware that you will accept anything and give them an address and telephone number of someone to contact (someone who is home a 1ot). Effective negotiating skills, diligence, and persistence can make a big difference in the level of sponsorship and amount of donations.

Be sure to have donated items catalogued as they are promised and as they arrive or are picked up. This helps to follow up on promised items not received. It also helps to gauge the size of the events in which the donated items will be used (auction, raffle, etc.) and ensures that all donors will be formally thanked after the convention, which is critical.

When the items arrive, you can then determine where they will be best suited.

Check with the Chamber of Commerce in your area, banks and any Convention bureaus for a list of prospective companies. Contact pet stores, order houses, aquarium set-up and maintenance companies, and manufacturers of aquatic supplies for donations. Check local manufacturer's, retail stores etc for sponsorship.

Acknowledge sponsors when ever possible (auction, show bulletins club bulletins etc.) Do not forget to send out thank you letters to each donator and vendor. Failure to do this follow-up, after Convention task is considered by many vendors a breach of unwritten protocol and can seriously affect vendor support in the future.

Vendors have often donated all the goods that they have remaining when they are ready to leave the Convention. Arrange in advance to collect these items from the vendors, whether for use in an auction, raffle or to be distributed freely. Even with prearrangements, vendors sometimes just hand the goods out on a first come first served basis or just leave them behind on the tables when they go, which can lead to most of the goods going into the hands of just a few.

AUCTIONS

Due to the many particular requirements for conducting well organized, successful auctions, an Auction Coordinator should be named for each auction. (If separate silent and live auctions are to be held, then a different Auction Coordinator might be appropriate for each event). A list of suggested Auction Coordinator responsibilities is listed at the end of this section. More than one auction might be conducted, with fish and new equipment and supplies in separate or combined auctions and a plant auction. You will need one or more cashiers and probably a data entry person to keep track of sales transactions for each auction. The Convention Treasurer should understand and be satisfied ahead of time with the cash management processes the Auction Coordiantor(s) intend to use. The auction format may use auctioneers or written bids as a format. With written bids adequate time must be allowed to allow bidders the chance to run up the prices.

For live auctions, at least two auctioneers are necessary to allow reasonable rest periods for each auctioneer.

The greatest workload is at the close of the auction when all or many bidders will be paying for their purchases.

Because some bidders will want to bid on many items and not stop to pay for each item right after it is won, consider running tabs for those that ask for one.

Make sure the auction room is large enough, with a good supply of display tables.

Allow ample time for your auctions. This is very important.

If any computer program is used for any auction a dry run/dress rehearsal prior to the actual auctions is appropriate to avoid problems during the auction(s).

Have all show items to be auctioned tagged or indelibly marked with a unique Auction Item Number so they can be easily handled and transactions completed and recorded quickly. It is helpful, especially for future planning, if a brief description of the item is included.

For Silent Auction items, each item should have a bid sheet that is marked with the Auction Item Number, the seller, and a description of the item. Without this info, you will not be able to track sales later, which can be valuable in assessing the auction. The bid sheets need to be made up well ahead of the Auction. Unless the Bid sheet and item have matching unique Auction Item Numbers, you cannot tell if a buyer is paying the right amount for the item in hand.

For live auctions, a recorder must be used to record the Auction Item Number, Buyer/Bidder Number, and sales price of each item as it is sold or alternatively, runners may fill out a card with that information, handle the sales transaction with the buyer and then immediately turn the card in to the data entry person to record the information in the computer.

Provide a refreshments table if at all possible and reasonably affordable; this is a good way to keep people from wandering off.

There are several ways to run the auction: a) cash & carry system, where several runners equipped with aprons and a small cash float deliver the purchase and receive payment, b) lot system, where each bidder receives a number which corresponds to a box in which are placed the bidders purchases. This makes the tabulation easier, making payment easier and then enables you to pay people their split at the auction, thus decreasing your mailing cost. Whatever auction system is used, it should be discussed with the AGA Board well in advance of the convention so that as much experience as possible con be brought to bear on this event.

If using the lot system, try to approach a supplier who will donate boxes as a form of advertising, also have a good supply of p1astic bags (grocery type, etc) available for purchases.

The auction room is a good place to display posters thanking donors and sponsors. The more you recognize a vendor, the easier it will be to gain the support of the vendor at subsequent conventions.

Remember to make good use of frequent advertising and get the public involved.

A sales table (where consignors specify a price for each item) is another way of reducing pressure on the main auction. Having an experienced auctioneer can greatly affect how quickly a Live Auction proceeds and how high the average price per items will be.

You have to decide how large an auction you can accommodate or want given basic facilities and time restraints and what you can reasonably expect. Varying the split (i.e. club/consignor) may increase or decrease the number of items you receive.

Make sure that regardless of the order in which they are submitted; all live consignments are sold.

Allow attendees the option to move an item forward in the auction for a small fee, e.g., $2. Someone should be in charge of collecting this money and getting the respective lot to the auctioneer immediately.

Don’t forget, that you will need for the auction(s) things like a personal computer, printed receipts, calculators, staplers, pens, a sales form to document buyer's information, a sign for credit card purchases (if arrangements have been made with a credit card processor bank to handle credit card payments), shopping bags or cartons, bidding sheets (for last minute entries/donations to the silent auctions). One or more of these items is very likely to be forgotten!

Decide if you will have one or more cashiers/cash drawers for each auction, whether silent or live auction. A single cashier/drawer for all auctions greatly simplifies end of auction reconciliation and minimizes staffing requirements but makes it much harder to determine afterwards, which auction produced what revenues. Using unique Auction Item Numbers across all auctions, and recording these numbers with each sale allows the capture of all the information while using as few as one cashier.

Have an initial cash supply at the start of sales so that cashier(s) can make change.

Be sure every check, when offered as payment, is made out correctly and to the correct party.

Consider having any silent auctions take place in the vendor area and try to include as many activities as practical in the vendor area to promote traffic and contact between the registrants and the vendor representatives.

AGA Auction Coordinator Responsibilities:

Prior to the conference:

- Assist the Conference chairperson as needed in coordinating acquisitions of donations for the auction.

- Collect all items needed for auction/check out process;

- moving carts to transport items to/from rooms

- Documents to copy/distribute:

- Silent Auction Guidelines/Auction Registration Forms (can be sent out with brochure/ reg. Confirmation)

- Auction Bid Sheets

- Sales Receipt Forms

- 3 calculators

- 3 staplers and extra staples

- many pens to distribute for auction use

- Print out several Sales Receipt Forms to document buyer/donor info, signatures for credit card purchases, document reimbursement status, etc.

- Label stickers to label each shopping bag with attendee's name

- Just before the conference, obtain a copy of the attendee list to make the check out process quicker.

During the conference:

- FRIDAY 12:00pm - 6:00pm. Assist volunteers at the registration desk to accommodate attendees who may be bringing auction items at that time. Distribute the Silent Auction Guidelines to attendees and answer questions. Complete Auction Registration Forms for sellers and secure these forms for auction records. Make sure all plant donations are labeled with SCIENTIFC NAME, COMMON NAME (if known), VARIETY and DONOR'S NAME. If the auction items cannot be received at this time, arrange another time BEFORE SUNDAY MORNING to receive them. Storage/security of all auction items is the responsibility of the Auction Coordinator.

- SATURDAY 8:00am - 4:00pm. Continue to be available to receive auction items, process forms and secure items in storage.

- SUNDAY 7:30am – 10:00am. Coordinate all aspects of the Silent Auction set up. Hopefully you will have at least 4 volunteers to assist with completing bid sheets, distributing items and labeling shopping bags.

- SUNDAY 10:00am until?  The Auction should promptly begin at 10:00am and an assigned announcer will coordinate the auction process. For auction rules, refer to the Silent Auction Guidelines handout. Attendees may wish to check out before the auction is over, hence the need for several volunteers prior and during the auction.

- After all attendees are checked out, unsold items must be packed up for the AGA to remove.

After the conference:

- Organize bid sheets and tally auction income and reimbursement to donors.

- Cross-reference income with Sales Receipt Forms. Save bid sheets and registration forms.

- Make a copy of the Sales Receipt Forms and submit results to both the Conference Chair and the AGA Treasurer.

- Send all checks and a cashier's check of the total cash income to the AGA Treasurer as quickly as possible to expedite reimbursement to donors.

HOTEL

Since the contract with the hotel will determine dates, location and registration and banquet pricing, the contract should be negotiated as far ahead of the expected convention date as possible. Have one person deal directly with the hotel; keeping all correspondence and getting everything in writing! This will help keep problems to a minimum. Watch for hidden costs – for example, labor fees for hooking into the hotel public address system even if you hook in yourself. Try to anticipate everything. Do not make any financial commitments without express approval from the AGA Board of Directors or its designee.

Begin by making a list of suitable hotels in your area. “Suitable” meaning large enough, convenient by plane, bus, etc., and having a good reputation.

Determine what exactly your requirements are. Read over previous Convention reports to help get an idea of the number of people attending, and the number of entries for the fish room. Rooms will be needed for the following:

- Registration (Thurs & Fri. afternoon)

- Breakfast and/or Lunch options at Hotel for convenience (Sat.)

- Vendor displays (Sat. only)

- Speaker presentations (should accommodate at least 150 people)

- Banquet room (Sat. evening event) – Consider options for an off-site/ alternate location for the banquet, taking transportation options into consideration

- Breakfast option at Hotel for convenience (Sun. morning)

- Panel Discussion (Sun. morning)

- Auction(s) (Sun. morning-hall must be available by 7:30a.m. through early or late afternoon, depending on size and number of auctions)

The auction room must be large enough to accommodate several large tables and plenty of seating if it the format is a sit-down auction with auctioneers. Remember that a pubic address system will be needed.

Determine the size of your room where auction items will be setup and stored prior to the auction(s). It must be secure, temperature controlled, have easy access to water supply if fish are among auction items, and have easy access for entries to be brought in.

Determine the size and number of rooms required for the speaker forums. It/they must be large enough to accommodate a medium group of people and have public address equipment and perhaps visual equipment. Can the hotel supply these?

A banquet hall will be needed for Saturday and Sunday with ample room to set up. This might include a speaker presentation requiring Audio/video equipment, awards tables, and a cash bar. A vendor are will be needed that is as close to the speaker rooms as possible to ensure high traffic through the vendor area.

Send a letter to each hotel on your list, stating your requirements and requesting a quote from them. State the date by which these tenders are needed and that you will be making a shorter list based on the responses. These will be contacted by phone to arrange an inspection of their facilities. Also state the date of the final decision.

Let the hotel take care of all room registrations. Check for the extent and availability of (hopefully free) parking.

Ask the hotel to provide registration forms that can be included in the Convention brochure

Try to get the hotel to give you as many free rooms (for speakers) as possible to sponsor an early bird draw or anything else you can think of.

Request a menu selection well in advance, so you have an idea what is available. Obtain a menu before making a final decision on the hotel. Menu prices at hotels differ, sometimes substantially.

Set a per-person budget for the banquet (including tax & gratuity) but do not decide upon and confirm the menu until the hotel is prepared to guarantee the price in writing.

Develop as specific a list of requirements as possible. Anything you leave out might end up being an extra added charge (even an extension cord)!  With these requirements in hand take a few people to each hotel on your short list noting each ones good and bad points, so a decision can be made which is the most suitable. Eliminate immediately any that do not meet your minimum standards.

Try to get a price that will allow as many people to a room as desired.

The planning involving the hotel must consider and provide support for the needs of every aspect of the events and their setup, from table & chair layout to food service (include a contract proposal from the hotel regarding options on room rates, discounts, food service, etc.)  Whoever performs these tasks must be present during the Convention to ensure the arrangements are carried out correctly and on time.

Marketing, Publication and Advertising

Contact local newspapers, radio stations by letter a few months before the Convention and follow-up by telephone or person a week before.

Cable TV sometimes allows interviews to be taped and run several times.

Print small flyers for pet shops, schools, factories, Laundromats, libraries, etc.

Contact magazines, periodicals with an ad promoting the Convention.

Ask club editors to include their bulletins in your flyers.

Visit local clubs and send as much information as possible to out-lying clubs to generate more enthusiasm.

Prepare a slide presentation to be given or sent to other clubs to encourage regular club members to attend.

A hospitality suite or room helps break the ice and gives newcomers a place to meet other hobbyists. Consider a small cash bar. Set out munchies and set a reasonable time limit on the room. It’s a good place to hand out items donated by corporate sponsors for this purpose.

Give your raffle(s) general appeal. Not everyone is interested in the same thing. Have tickets available early and promote them heavily. Promote the sale by offering a free ticket for each book sold or a prize for the most tickets sold. Cut cost by printing them yourself, but be sure to keep the quality good, that helps sell tickets. Some have small raffles throughout the Convention, but beware not to flood the market. You may need a license, so check out local and provincial/state regulations.

Consider a tour of local aquatic related sites or shopping expedition. Make sure it has a general appeal.

At the convention, make appropriate use of signs to help attendees understand where things are located, when things will occur, and any important changes in schedule.

The AGA Convention Banner should be hung in a prominent location; prior arrangements will need to be made with the hotel. One of the AGA Board members will be able to make the Banner available to the convention staff.

Vendor Room

A key element of the convention is the area where vendors can display goods and information and vendor representatives can meet and speak with attendees. Ensuring high traffic in the vendor area is crucial to the success of the vendor area for the attendees and the vendors. The vendor area should be as close to the speaker/presentation rooms as possible. If possible, the registration desk, hospitality area, sales table, or other event functions should be incorporated into the vendor area.

Sales Table

AGA will want to have a sales table to vend various items such as Tshirts. This can be done jointly with convention staff if convention items are going to be offered or separately by AGA staff alone. This table is probably best located in the vendor area.

Speaker PROGRAM

There should be one keynote speaker, preferably with an international reputation, and four other speakers. Too many speakers means too little time for attendees to meet and chat with each other, visit the vendors, and talk to speakers outside of the presentations, which helps keep the presentations from overrunning their allotted time in the schedule. Seek out speakers who represent the planted aquarium industry as well as other experts (professional and amateur or knowledgeable hobbyists) with diverse topics.

The Convention usually subsidizes the keynote and, if possible, each speaker’s Convention registration fee, hotel room, transportation between the Convention and the airport (gas mileage should be paid before they leave), banquet charge deferred, and a small gift as a token of our appreciation, to be presented at banquet. The keynote speaker’s airfare to and from the host city should be paid by the Convention.

Telephone contact initially will speed up the speaker selection process. Send a follow-up letter. Request that they book early for air reservations (there may be savings here).

After speaker has confirmed in writing, they should be kept informed of the Conventions schedules and sent a Convention brochure. Request curriculum vitae for information for the Convention bulletin and the introduction at their presentation. Also request a photo in time to be used in the brochure, the AGA website, and out marketing efforts.

While it is generally advisable to minimize the number of contacts dealing with a speaker, the person responsible for producing the Convention Program should be allowed to contact speakers as necessary to complete the Program on time.

Speaker(s) may include one or two local persons. This helps keep costs low. Also, seek corporately sponsored speakers (e.g., the Marineland speaker program, or other vendors who are willing to give a talk such as Seachem)

Make sure the speakers are aware of the terms of their agreement, in writing, prior to Convention. Keep informed of their arrival and departure times and arrange to pick them up, if necessary. Make sure they get settled in and that he/she knows where and when they will give their talk. Make a list in advance of all equipment (public address, visual aid, automotive, etc.). Arrange for the equipment well in advance so that it will be available and setup when needed.

Be prepared to give a brief introduction before each speaker’s presentation.

Assign a host to each speaker for the duration of the Convention. The host need not be with the speaker at all times but should help the speaker keep track of time during their talk by giving them a 5 minute warning. Most important, they are a person the speaker can turn to at any time with questions or needs. They do not have to dine with the speaker, but they should make sure the speaker has someone to dine with, and that the speaker does not feel left out. The hosts should introduce themselves to their assigned speakers via email in advance and ensure the speakers’ travel, hotel, and audio/visual needs will be met. They should also responsible for appropriate speaker introductions to be delivered by the MC or themselves and to help their respective speaker avoid going over their time limit for their presentation.

If Aquascaping Contest Awards are to be announced at the convention and the judges will be asked to comment on the wining entries, make sure the judges are aware of this ahead of time so that they can be prepared to comment. It might help to remind the judges that people tend to hear negative comments more strongly than positive comments.

Remember to check all equipment for malfunctions before the convention begins and check the equipment to be used in a presentation before the presentation begins.

REGISTRAR /REGISTRATION

Someone must be readily available by phone, mail, e-mail, and fax 6 months prior to Convention to answer questions and receive registrations. This person must keep copies of each registration and check or money order received before forwarding to the treasurer. A Master list of all Convention attendees, including speakers, paid registrants, vendors and compensated volunteers must be compiled to submit an accurate count to the hotel of the numbers of participants for each event. Three copies of this Master list should be available at the registration desk to assist attendance documentation, confirm attendee information, and later facilitate recording auction purchases. One of the lists should be posted near the registration table to aid attendees in meeting each other. This is a good place to post a list of tables before the banquet so that each attendee can sign up for their preferred table.

Registrants should know before they arrive when registration will begin and a sign or signs should be clearly posted so that every attendee can easily know when registration begins. It is very important that registration staff be present and registration occur at the appointed times. Especially if there is a filed trip organized for early Friday, registration should be open on Thursday.

AT the registration table, have name tags for all preregistered attendees and a few blank tags for day-of-Convention registrants. Name tags should be made two to three days prior to the Convention. If possible, put a concise version of the Convention schedule on the back of the name tags. Packets with name tags, Convention schedule, promotional flyers, hospitality items, etc., should be assembled for each attendee just prior to the Convention and made available to those working the registration desk. This will require coordination between the person handling vendor donations and the Registrar. The name tags for key convention personnel should have some clear markings so that attendees will know that they can go to these people if they have questions during the convention.

When attendees get their registration packets, ask if they are first time AGA or fish convention attendees and record this information. Have some convention staff assigned the responsibility of informally checking on these people every now and then to ensure that they feel “at home”, asking them whether they need anything or have any questions and do they have plans for lunch.

Let the hotel handle all room registrations. Mention the cut-off date frequently if there is a discount or special prize for early registrations.

Offer several different packages 1) weekend single/double 2) single Fri/Sat 3) single Sunday banquet 4) speakers (if not complimentary).

Set the price to make it appealing and economical.

To help keep your records straight, do not accept any registrations from other people not filled out on a form. If it is taken at a meeting or over the phone still fill it out or write all the information down, this will cut down on errors. This information is very important.

Receipts can be mailed.

Expect many last minute sales. The last week you will need to stay by the phone.

Have a sign stating when and where registration takes place in a prominent location (near the hotel front desk). When people arrive and have secured their room, the first thing they want to know is, “Where do I register or sign in?” Have information about the hotel layout, Convention events and local area close at hand. A small card file at the registration desk to place information as guest’s sign in (room number, who’s with them, etc) is very handy. Consider having a Hospitality Opener for the start of registration.

At the convention, it is advisable to have a PC at the registration desk where attendees will sign in or walk-ins pay for registration. This will allow a quick look up of registration status, AGA membership, etc. without undue delay. Since walk-ins are likely, a cash drawer, receipts, and a reliable means of recording purchases needs to be set up at the registration/sign-in desk. Post a roster of convention attendees near the check-in table.

The Registrar’s list(s) of registrants, Field Trip, and Banquet attendees should be reconciled with the Treasurer’s list of transactions on an ongoing basis before the convention to avoid errors and ensure consistency.

TREASURER

This person need not be your club treasurer. The person must be competent and reliable to handle large sums of money accurately, maintain exact records, and prepare the appropriate budget and reporting materials. The Treasurer should be in close contact with the Chairperson, AGA Treasurer, Registrar, Auction Coordinator(s), other host club staff as appropriate, and the AGA Board.

Establish a Convention budget early and determine how much you will be able to spend and where money should be channeled, e.g.

Room rentals, Meals, hospitality suite, auctioneer, Publicizing the Convention & Publishing Convention Brochures, Raffles, prizes, etc.

Some upfront money will be needed, but check into invoicing terms on larger items. You may get a discount if paid within a certain time limit. Also, ensure you have enough money to pay immediate expenses.

Arrange with the hotel’s representative shortly after the Convention to review their charges. Review their bill carefully. Mistakes can be costly.

Setting a budget for each area is useful. Work out an estimated profit and loss statement/budget even before you make your bid. Also make a worse case scenario budget (e.g. make high estimates of costs and low estimates of revenues) and see if the Convention breaks even. This is a great comfort for club members.

Several suggested accounts for the bookkeepers records are 1) advertising, 3) Convention registration, 4) auction, 5) raffle, and 6) program and hospitality suite.

For out of country entries, allow for reasonable exchange rates.

Accept checks (from persons known to the club) for auction items. Consider arranging for accepting credit card payments for auction items – be sure to factor in the transaction costs in the financial plan. People spend more if they do not have to keep track of the cash they have on hand.

As soon as the details are established, the Treasurer should inform those persons involved in preparation of any printed matter regarding registration of the payment methods that can be used and how payments should be made.

One method of tracking Convention monies is for the host club to set up a bank account for the convention. If an account is set up, it should be a business account so that checks made out to AGA, AGA Convention, AGA2K4, can be processed through the account. If the account is set up as a personal account, then it is possible that only checks made out to an individual can be processed through the account under the banking laws that apply in most states.

Equipment Manager

This should be someone local to provide, for example,  a working laserjet or good inkjet printer and computer system to handle any requests for name tags, signs, auction related items, etc. This person should also acquires cardstock for badges and signs,  receipts for use in the auction(s),and other office-supply needs.

Additional Information Regarding the 5th AGA Convention

The following people have offered their services:

Erik Olson	Producing and Directing Video Taping and providing some Public Address equipment (including microphones, mixers, and other audio gear) for events. Editing and production of recorded materials; assistance with any integration between the convention and the AGA Aquascaping Contest, including printing of photos

Scott Hieber	Gaffer, assistant cameraman

Cheryl Rogers	Registration management

Scott Hieber	Convention Treasurer, including assistance in preparing Budget Planning and reporting, tracking revenues and expenses and preparing any financial analyses that might be useful.

Phil Edwards	Assistance with vendor solicitation.

The AGA will establish a private web mailing list including the AGA Board and the Host’s convention staff to help maintain communications and provide for discussion of any issues as they arise.

The AGA Executive Board can assist with selecting speakers.

AGA Silent Auction Sales Receipt Form			Date: _______________

Name: ______________________________ 			Amt.  $ _________________

______________________________  Payment by: Cash     Check       CC 

______________________________ CC #  _______________________ Exp. _______

 CC SIGNATURE : _________________________________________________

Name: ______________________________ 			Amt.  $ _________________

______________________________  Payment by: Cash     Check       CC 

______________________________ CC #  _______________________ Exp. _______

 CC SIGNATURE : _________________________________________________

Name: ______________________________ 			Amt.  $ _________________

______________________________  Payment by: Cash     Check       CC 

______________________________ CC #  _______________________ Exp. _______

 CC SIGNATURE : _________________________________________________

Name: ______________________________ 			Amt.  $ _________________

______________________________  Payment by: Cash     Check       CC 

______________________________ CC #  _______________________ Exp. _______

 CC SIGNATURE : _________________________________________________

_________________________________________________

Name: ______________________________ 			Amt.  $ _________________

______________________________  Payment by: Cash     Check       CC 

______________________________ CC #  _______________________ Exp. _______

 CC SIGNATURE : _________________________________________________

_________________________________________________

- These Silent Auction Guidelines, Auction Registration Form and Auction Bid Sheet documents are samples provided for information purposes for the benefit of prospective convention sponsors –

Aquatic Gardener Association

Silent Auction Guidelines

When Convention attendees pick up registration packets, an Auction Coordinator will be at the convention registration table to assist auction donors in processing items, completing the auction forms and confirming whether the proceeds are full donations (i.e., that the AGA will receive 100% of the proceeds) OR that the donor confirms a partial (50%) profit, with the other 50% as proceeds to the AGA. Plant material as well as related items will be accepted. Each donor (vendor) may submit a maximum of 10 (lots) with no more than 4 lots of any one species or variety. We encourage you to bring unusual or hard-to-find plants to ensure a great selection. PLEASE pre-label all plant bags with a scientific name, a common name (if known) and the donor’s name. If the Auction Coordinator cannot process all auction items at the time of registration, another time BEFORE SUNDAY MORNING should be determined by the Convention Chair and the Auction Coordinator. Storage of the auction items will be the responsibility of the Auction Coordinator.

On Sunday, Auction volunteers place the items on several designated tables with a corresponding bid sheet to the right of the item. ACCESS DURING AUCTION SET UP IS RESTRICTED TO THE AUCTION COORDIANTOR AND AUTHORIZED AUCTION VOLUNTEERS. The silent auction will begin promptly at 10:00 a.m.

Silent Auction Rules:

- Auction attendees will be given the opportunity to inspect all auction items for a fixed amount of time set by the Auction Coordinator. A bidder does not need to register for the convention or the auction to bid. Each bid must be a multiple of ONE DOLLAR. A bidder submits a bid by writing her or his name and the bid amount on the corresponding items’ bid sheet. ONLY LEGIBLE BIDS WILL BE DEEMED VALID. There is no limit on the number of bids that may be placed on any item with in the allotted time for placing bids.

- To finalize bids, the Auction Coordinator or an Auction Volunteer will announce to bidders when a table will be closed to bidding. An announcement of the bid opening period for each table will be made by the Auction Coordinator. An announcement of the bid closing time for a table will be made at the start of the bidding period, at 5 minutes before the close of the bidding period, and at the close of the bidding period. After the closing of the bidding period for a given table, no further bids may be made on items on that table nor will any further bids be accepted on those items. Auction Volunteers will remove and sort items for winning bidders. PLEASE DO NOT INTERFER WITH THIS PROCESS OR GO BACK TO THE CLOSED TABLES. Bidding continues on remaining tables until each is closed to bidding.

- Payment for AGA auction items can be made by cash, check and possibly by Master Card or Visa if arrangements with a credit card processor have been established. All bidders must check out and pay during or immediately after the auction concludes. Cashiers will be available to retrieve your bag(s) of items and check you out. The AGA Treasurer will be responsible for mailing checks for sellers’ portions of auction revenues within 2 weeks following the auction.

- Any unsold items must be retrieved by the seller immediately after the auction or they will be considered a donation to the AGA.

PLEASE SEE AUCTION REGISTRATION FORM ON THE REVERSE SIDE OF THIS SHEET

Aquatic Gardener Association

Auction Registration Form

Donor/Seller Information

Name :    __________________________________

Address: __________________________________

City:        ____________________________ State : ______ Country : _______

Zip or Postal Code : _______________  E-mail : ________________________

Phone # : ________________________

List of Auction Items:

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

- _____________________________________________________________________

AGA SILENT Auction Bid Sheet

ITEM #:  ______________DONOR/SELLER :  _______________________________

Genus species (var.): ____________________________  Common Name: ______________________

BIDS MUST BE IN MULTIPLES OF $1.00.   PRINT CLEARLY USING INK.

Name	Bid Amount

1. _______________________________________			        1. _____________________________

2. _______________________________________			        2. _____________________________

3. ______________________________________			        3. _____________________________

4. _______________________________________			        4. _____________________________

5. _______________________________________			        5. _____________________________

6. ______________________________________			        6. _____________________________

7. ______________________________________			        7. _____________________________

8. _______________________________________			        8. _____________________________

9. _______________________________________			        9. _____________________________

10. ______________________________________			      10. _____________________________

11. ______________________________________			      11. _____________________________

12. ______________________________________			      12. _____________________________

13. ______________________________________			      13. _____________________________

14. ______________________________________			      14. _____________________________